## Sheet1
Schedule or Process |  |  | Functional/Systems | Product |  |  | Human | Geospatial | Contextual
Time [Month] | Ship_LC | Process | Systems | Digital | Resulting Vessel Data | Physical | Team | Location (Country)
1 | Concept Phase | Requirements and Specification Definition | Transitional | Preliminary Ship Specification Document |  | NA | Design Team | Ulsteinvik | Business Trends
1 | Concept Phase | Requirements and Specification Definition | Transitional | Preliminary Ship Specification Document |  | NA | Finance Team | Ulsteinvik | Business Trends
1 | Concept Phase | Requirements and Specification Definition | Transitional | Preliminary Ship Specification Document |  | NA | Business Development Team | Ulsteinvik | Business Trends
1 | Concept Phase | Configuration Development | Hull Form | Principal hull dimensions |  | NA | Design Team | Ulsteinvik | Reference Data, Rules, Best Practices
1 | Concept Phase | Configuration Development | Configuration Evaluation | Deckhouse Configuration Sketch |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Configuration Development | Configuration Evaluation | General Arrangement Sketch |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Configuration Development | Configuration Evaluation | Topside Arrangement Sketch |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Configuration Development | Configuration Evaluation | Appendage Configuration Sketch |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Mission Systems | Description of mission-critical systems and features |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Mission Systems | Estimates of critical performance aspects |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Mission Systems | Manning estimate |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Mission Systems | Essential performance requirements |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Structural Analysis | Structure |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Vessel Performance | Propulsion plant type |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Vessel Performance | Electric Plant |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Configuration Evaluation | Fluid Systems |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Systems Design and Analysis | Configuration Evaluation | HVAC Systems |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Systems Design and Analysis | Configuration Evaluation | Auxiliary Machinery & Mechnical Systems |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Systems Design and Analysis | Configuration Evaluation | Outfit and Furnishing |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Total Ship Analysis I | Vessel Stability | Area/Volume Summary |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Total Ship Analysis I | Vessel Stability | Weight/KG Estimate |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Total Ship Analysis I | Vessel Performance | Installed Electric Generating Capacity |  | NA | Design Team | Ulsteinvik
1 | Concept Phase | Total Ship Analysis I | Configuration Evaluation | List of major equipment |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis I | Cost Analysis | Cost estimate |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis I | Risk Analysis | Technical and Managerial Risk Plan |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Speed/power estimate |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Manuevering |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Seakeeping |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Stability | List, Trim, and Freeboard |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Stability | Intact Stability Check |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Stability | Floodable Length and Damage Stability |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Stability | Payload Definition |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Endurance fuel estimate |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Noise Analysis |  | NA | Design Team | Ulsteinvik
2 | Concept Phase | Total Ship Analysis II | Vessel Performance | Vibrations |  | NA | Design Team | Ulsteinvik
5 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Ship specification |  | NA | Accommodation Team | Poland
5 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Lines Drawing |  | NA | Accommodation Team | Poland
6 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Appendage Drawing |  | NA | Accommodation Team | Poland
6 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | General Arrangements |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Outboard Profile |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Inboard Profile |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Topside Arrangement |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Capacity Plan |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Stability | Weight Report |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Ship Structures | Structural Design Criteria Manual |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Ship Structures | Midship Section |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Ship Structures | Steel Scantling drawings |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Machinery Control System Diagrams |  | NA | Accommodation Team | Poland
7 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Propulsion and Auxiliary Machinery |  | NA | Powering Team | Poland
8 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Propulsion Shafting Arrangement |  | NA | Powering Team | Poland
8 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Propeller Design |  | NA | Powering Team | Poland
9 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Electric Load Analysis |  | NA | Powering Team | Poland
9 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Electric Power and Lighting Systems Diagrams |  | NA | Powering Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Fault Current Analysis |  | NA | Powering Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Navigation System Diagram |  | NA | Electrical Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | HVAC Load Analysis and Design Criteria |  | NA | Electrical Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Ventilation and Air Conditioning Systems Diagrams |  | NA | Electrical Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Piping Systems Analysis |  | NA | Electrical Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Diagrammatic arrangements of all piping systems |  | NA | Electrical Team | Poland
10 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Fire control diagram by decks and profile |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Mechanical Systems Arrangements |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Living Space Arrangements |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Commissary Space Arrangements |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Working Space Arrangements |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Interior Communications System Diagram |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Detailed Master Equipment List (MEL) |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Preliminary Ship Manning Document |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Pollution Control Systems Report |  | NA | Electrical Team | Poland
11 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Stability | Loading Conditions |  | NA | Design Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Stability | Floodable Length Curves |  | NA | Design Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Stability | Trim and Stability Booklet |  | NA | Design Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Stability | Damage Stability Analysis |  | NA | Design Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Endurance Fuel Analysis |  | NA | Powering Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Vessel Performance | Hydrodynamic Model Test Results |  | NA | Powering Team | Poland
12 | Detailed Engineering | Detailed Design, Analysis & Simulation | Configuration Evaluation | Stack Gas Flow Analysis |  | NA | Design Team | Ulsteinvik
13 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Evaluations of other aspects of required performance |  | NA | Design Team | Ulsteinvik
13 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Availability Analysis |  | NA | Design Team | Ulsteinvik
13 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Maintenance Plan |  | NA | Design Team | Ulsteinvik
13 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Supportability Plan |  | NA | Design Team | Ulsteinvik
14 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Crew Training Plan |  | NA | Design Team | Ulsteinvik
14 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | T&E Plan |  | NA | Design Team | Ulsteinvik
14 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Safety Analysis |  | NA | Design Team | Ulsteinvik
15 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Procurement Specifications |  | NA | Design Team | Ulsteinvik
15 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Models and Mockups |  | NA | Design Team | Ulsteinvik
15 | Detailed Engineering | Detailed Design, Analysis & Simulation | Cost Analysis | Cost Estimate |  | NA | Design Team | Ulsteinvik
16 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Technical Risk Assessment |  | NA | Design Team | Ulsteinvik
16 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Initial Regulatory Body Review |  | NA | Design Team | Ulsteinvik
16 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Building Plan |  | NA | Design Team | Ulsteinvik
16 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Budget Control List |  | NA | Design Team | Ulsteinvik
16 | Detailed Engineering | Detailed Design, Analysis & Simulation | Transitional | Production Plan |  | NA | Design Team | Ulsteinvik
Steel Construction
Parts Fabrication
On-block outfitting
Onboard outfitting
Launching
Delivery and Testing
Commissioning
PART_OF
SCHEDULEDTODELIVERY_BY
PRODUCED_INTO
GENERATED_BY
TEAMBASED_AT
PRODUCED_AT

## Inputs
Departments from Ulstein | Locations
Design Team | Ulsteinvik
Structural Team
Accommodation Team
Machinery Team
Electrical Team
Powering Team
Finance Team
Business Development Team

## Sheet2
Sources:
Andrews et al, 2006
Bruce, G., 2021
Gale, 2003
Based on Ulstein